## 🏠 Dashboard
BLUSHES & BRUSHES
Summer 2026 Lead Generation Campaign — Command Centre
Total Leads | Trials Booked | Enrolled | Total Spend ₹ | Avg CPL ₹ | Revenue ₹
QUICK NAVIGATION
→ ✅ Setup Checklist | Track all technical setup tasks
→ 🎬 Content Tracker | Track every video from filmed to posted
→ 📅 Weekly Ops | Day-by-day task calendar for 8 weeks
→ 📲 Lead Follow-Up SOP | Step-by-step WhatsApp follow-up guide
→ 💰 Budget Tracker | Track ad spend, leads, and cost-per-lead
SUMMER CAMPAIGN GOAL
Budget | ₹5,000 – ₹10,000/month (₹165 – ₹330/day)
Target Leads | 50–150 leads per month
Target CPL | Below ₹150 per lead
Trial Conversion | 40–60% of leads → trial class
Enrolment Rate | 30–50% of trial attendees → enrolled
Campaign Period | May – August 2026 (Summer)
Landing Page | Paste Vercel URL here after deployment →

## ✅ Setup Checklist
BLUSHES & BRUSHES — MASTER SETUP CHECKLIST
Summer 2026 Lead Campaign ¦ Mark tasks Done as you complete them
# | Category | Task | Who | Effort | Status | Notes / Link
1 | Landing Page | Confirm landing page runs on localhost:3000 | Dev | 5 min | ✅ Done | Run: npm run dev
2 | Landing Page | Deploy to Vercel (free tier, no domain needed) | Dev | 10 min | 🔄 In Progress | vercel --yes --prod
3 | Landing Page | Add live Vercel URL to this sheet in Notes column (row 2) | Both | 2 min | ⬜ To Do | Paste URL when deployment done
4 | Landing Page | Test form submission end-to-end on live URL | Both | 5 min | ⬜ To Do | Fill form → check Google Sheet
5 | Landing Page | Share live URL with Urvashi for review | Dev | 2 min | ⬜ To Do | WhatsApp or email
6 | Meta Pixel | Go to Meta Events Manager → Create Data Source → Web Pixel | Urvashi | 10 min | ⬜ To Do | business.facebook.com → Events Manager
7 | Meta Pixel | Copy Pixel ID and paste into .env.local (NEXT_PUBLIC_META_PIXEL_ID) | Dev | 5 min | ⬜ To Do | Redeploy on Vercel after change
8 | Meta Pixel | Add Pixel ID to Vercel Dashboard → Settings → Env Variables | Dev | 5 min | ⬜ To Do | Also add WEBHOOK_URL there
9 | Meta Pixel | Verify Pixel fires on landing page using Meta Pixel Helper extension | Dev | 10 min | ⬜ To Do | Chrome extension: Meta Pixel Helper
10 | Automation | Create free Make.com account at make.com | Dev | 5 min | ⬜ To Do | make.com/register
11 | Automation | Create new scenario: Webhook → Google Sheets → WhatsApp | Dev | 30 min | ⬜ To Do | See playbook Part 3 for step-by-step
12 | Automation | Copy Make.com webhook URL → paste into WEBHOOK_URL env var | Dev | 5 min | ⬜ To Do | Vercel Dashboard + .env.local
13 | Automation | Create Google Sheet 'BB Leads' with columns: Timestamp, Name, Phone, Course, Source, Status, Notes | Urvashi | 10 min | ⬜ To Do | Share sheet edit access with Make.com
14 | Automation | Connect WhatsApp Business to Make.com (via Cloud API or WATI) | Dev | 20 min | ⬜ To Do | WATI 7-day free trial at wati.io
15 | Automation | Test full flow: submit form → row in Sheet + WhatsApp message | Both | 10 min | ⬜ To Do | Use a test phone number first
16 | Meta Ads | Confirm Meta Business Manager account is active | Urvashi | 5 min | ⬜ To Do | business.facebook.com
17 | Meta Ads | Create Ad Account inside Business Manager if not already done | Urvashi | 10 min | ⬜ To Do | Add INR billing method (UPI/card)
18 | Meta Ads | Create Campaign: objective = Leads, name = BB_Summer_Leads | Dev/Urvashi | 15 min | ⬜ To Do | Use landing page URL as destination
19 | Meta Ads | Create Ad Set 1: Women 18–24, 10km Ramesh Nagar, ₹100/day | Dev/Urvashi | 15 min | ⬜ To Do | Interest: Beauty, Makeup, Fashion
20 | Meta Ads | Create Ad Set 2: Women 25–40, 10km Ramesh Nagar, ₹100/day | Dev/Urvashi | 15 min | ⬜ To Do | Interest: Home beauty, Freelancing, Salon
21 | Meta Ads | Upload Angle A (Student) video to Ad Set 1 | Urvashi | 10 min | ⬜ To Do | 15-sec vertical Reel
22 | Meta Ads | Upload Angle B (Homemaker) video to Ad Set 2 | Urvashi | 10 min | ⬜ To Do | 30-sec landscape/square video
23 | Meta Ads | Set campaign start date and confirm payment method | Urvashi | 5 min | ⬜ To Do | Start immediately once ads are approved
24 | Instagram | Switch Instagram to Professional (Creator/Business) account | Urvashi | 5 min | ⬜ To Do | Settings → Account → Switch to Professional
25 | Instagram | Add landing page URL to Instagram bio | Urvashi | 5 min | ⬜ To Do | Paste Vercel URL in bio link field
26 | Instagram | Connect Instagram account to Meta Business Manager | Urvashi | 10 min | ⬜ To Do | business.facebook.com → Accounts → Instagram
27 | Instagram | Post first Reel (studio tour or course graphic) | Urvashi | 20 min | ⬜ To Do | Caption template in ad brief doc

## 🎬 Content Tracker
CONTENT CREATION TRACKER
Track every video and post from script → filmed → edited → posted
# | Format | Angle / Topic | Script Ready? | Filmed? | Edited? | Posted? | Post Date | Platform | Notes
1 | 15s Reel | Angle A — Don't Waste Your Summer (Hindi) | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Script in Brief doc p.3
2 | 30s Feed Ad | Angle B — Passion into Paycheque (Hindi) | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Facebook + IG Feed | Script in Brief doc p.4
3 | 15s Reel | Angle C — Career Switch (Hindi) | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Script in Brief doc p.5
4 | 10s Story | Angle D — Only 2 Seats Left (film WEEKLY) | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Stories + Reels | Re-film every Monday
5 | 45s Video | Angle E — Founder Story (Urvashi to camera) | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | IG + FB Feed | Most important — retargeting
6 | Reel | Studio tour — wide shot salon pan | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Shot #2 from shot list
7 | Reel | Bridal makeup before/after reveal | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Transformation = high shares
8 | Carousel | All 3 courses — course graphic carousel | ✅ Done | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Feed | Use existing course PNGs
9 | Reel | Nail art timelapse (any design) | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Top-down, tripod if possible
10 | Story | Student testimonial (screen-record DM or video) | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Stories + Highlights | Ask recent graduate
11 | Reel | Urvashi teaching student 1-on-1 | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Side angle, natural convo
12 | Post | Certificate ceremony — graduation moment | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Feed | Warm, celebratory caption
13 | Reel | 5 mistakes in bridal makeup (educational) | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Reels | Educational = saves = reach
14 | Story | FAQ polls: Which course? / Budget? / Experience? | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Instagram Stories | Poll stickers drive engagement
15 | Reel | Wk 7 — Last 2 Seats urgency (film fresh) | ⬜ To Do | ⬜ To Do | ⬜ To Do | ⬜ To Do |  | Reels + Stories | Film in week 7 specifically

## 📅 Weekly Ops
8-WEEK SUMMER OPERATIONS CALENDAR
Daily task breakdown by week ¦ Check off each week when complete
Week | Dates | Mon | Tue (Post) | Wed | Thu (Post) | Fri | Sat (Post) | Sun | Ad Check | Done?
1 | Launch Week | Film all shot list | Post: Studio Tour Reel | Edit videos | Post: Course Carousel | Upload ads to Meta | Post: Meet Urvashi video | Review ad performance | Launch Ad Set 1 + 2. Budget ₹200/day | ⬜ To Do
2 | Wk 2 | Reply all DMs | Post: Student testimonial | Film new content | Post: Day in the life | Film Angle D (fresh) | Post: Nail art timelapse | Review leads in Sheet | Boost top organic Reel ₹200/day | ⬜ To Do
3 | Wk 3 | Reply all DMs | Post: Before/after bridal | Check ad CPL | Post: 5 reasons Reel | Kill weak ad set | Post: FAQ Stories (polls) | Count leads this week | Kill ad set CPL >₹300. Double winner | ⬜ To Do
4 | Wk 4 | Reply all DMs | Post: Certificate ceremony | Prep Q&A Live | Post: ₹20k breakdown | Promote Live | Live Q&A 30 min on IG | Review pipeline | Launch Retargeting Ad Set (Angle E) | ⬜ To Do
5 | Wk 5 | Reply all DMs | Post: Student transform | Scale winner 2x | Post: Nail tutorial | Film Angle D (fresh) | Post: Seats filling up Reel | Count total leads | Scale best ad set to ₹300/day | ⬜ To Do
6 | Wk 6 | Reply all DMs | Post: New batch announce | Film BTS content | Post: BTS sourcing | Film Angle D (fresh) | Post: Founder Q&A Stories | Mid-campaign review | Run Angle D urgency ad separately | ⬜ To Do
7 | Wk 7 | Reply all DMs | Post: Last 2 seats Reel | Prepare closing ads | Post: Graduate story | Max budget winner | Post: Summer recap carousel | Count enrolled leads | Max budget on best performer | ⬜ To Do
8 | Wk 8 | Reply all DMs | Post: New batch announce | Prep next campaign | Post: Early-bird offer | Export leads list | Post: Thank-you video | Full campaign debrief | Lookalike audience from leads list | ⬜ To Do

## 📲 Lead Follow-Up SOP
LEAD FOLLOW-UP SOP (STANDARD OPERATING PROCEDURE)
Every lead that submits the form must go through all these steps in order
Step | Trigger | Who | Action | Time Limit | Script / Template | Status Track
1 | Form submitted | Make.com | Auto-send WhatsApp confirmation to lead | Instant | "Hi [Name]! 👋 Thanks for your interest in Blushes & Brushes! Urvashi will WhatsApp you shortly to schedule your free trial 💄 📍 Ramesh Nagar, Delhi ¦ 76784 46364" | Automated
2 | Form submitted | Make.com | Add row to Google Sheet BB Leads | Instant | Columns: Timestamp, Name, Phone, Course, Source, Status=New | Automated
3 | Make.com notifies Urvashi | Urvashi | Send personal WhatsApp voice note to lead | < 15 min | "Hi [Name], main Urvashi hoon, Blushes & Brushes se. Aapka interest dekh ke bahut khushi hui! Kya hum aapki free trial class schedule kar sakte hain?" | Manual
4 | Lead responded | Urvashi | Send 2–3 student photos + salon images | < 30 min | Share: best bridal result, happy student with certificate, studio shot | Manual
5 | Lead showed interest | Urvashi | Offer 2 specific date/time slots for trial | Same day | "Aapke liye Tuesday 11am ya Thursday 3pm — kaunsa better hai?" (Always give 2 options, not open-ended) | Manual
6 | Trial date confirmed | Urvashi | Send confirmation + address on WhatsApp | Immediately | "Confirmed! [Date] [Time] at Blushes & Brushes, B 1/1 Double Storey, Ramesh Nagar, Opp. Subway. See you then! 🎉" | Manual
7 | 1 day before trial | Urvashi | Send reminder WhatsApp | Day before | "Hi [Name]! Just a reminder — your free trial class is tomorrow at [Time]. Looking forward to meeting you! 💄" | Manual
8 | No response after 2 days | Urvashi | Send single polite follow-up | Day 2 | "Hi [Name], did you get a chance to think about it? The next batch has limited seats — happy to answer any questions 😊" | Manual
9 | Still no response D5 | Urvashi | Final follow-up with social proof | Day 5 | "Hi [Name], sharing a quick video of one of our recent graduates [share video]. Would love to have you visit 🙏" | Manual
10 | Trial attended | Urvashi | Follow up same evening for enrolment | Same evening | "So lovely meeting you today! Are you ready to join the batch? I can hold your seat for 24 hours 🌸" | Manual
11 | Enrolled | Urvashi | Add to WhatsApp batch group + update Sheet | Immediately | Update Google Sheet: Status → Enrolled. Add to batch WhatsApp group. | Manual
12 | Not enrolling yet | Urvashi | Add to nurture list for next batch | Within 1 wk | Update Sheet: Status → Nurture. Follow up in 3 weeks for next batch. | Manual

## 💰 Budget Tracker
AD SPEND & LEAD TRACKER — Summer 2026
Fill in Leads Generated and Trials Booked each week. All other columns auto-calculate.
Week | Ad Set / Channel | Daily Budget (₹) | Days Running | Spend (₹) | Leads Generated | Cost per Lead (₹) | Trials Booked | Enrolled | Notes
1 | Ad Set 1 — Students (Angle A) | 100 | 7 |  | 0 |  | 0 | 0 | Launch week
1 | Ad Set 2 — Homemakers (Angle B) | 100 | 7 |  | 0 |  | 0 | 0 | Launch week
1 | Boosted Post (top organic) | 0 | 0 |  | 0 |  | 0 | 0 | Only if strong organic post
2 | Ad Set 1 (continued) | 100 | 7 |  | 0 |  | 0 | 0
2 | Ad Set 2 (continued) | 100 | 7 |  | 0 |  | 0 | 0
2 | Boosted Post | 200 | 3 |  | 0 |  | 0 | 0 | Boost best Reel from Wk 1
3 | Ad Set winner (double) | 200 | 7 |  | 0 |  | 0 | 0 | Kill loser ad set
4 | Ad Set winner | 200 | 7 |  | 0 |  | 0 | 0
4 | Retargeting — Angle E | 65 | 7 |  | 0 |  | 0 | 0 | Page visitors
5 | Ad Set winner (scale 2x) | 300 | 7 |  | 0 |  | 0 | 0
5 | Retargeting | 65 | 7 |  | 0 |  | 0 | 0
6 | Ad Set winner | 300 | 7 |  | 0 |  | 0 | 0
6 | Urgency — Angle D | 100 | 7 |  | 0 |  | 0 | 0
7 | Max budget — winner | 400 | 7 |  | 0 |  | 0 | 0
8 | Lookalike from leads list | 300 | 7 |  | 0 |  | 0 | 0 | Export leads → create lookalike
TOTAL